## Sheet1
S.No | List of Tests | Location | Plan Start | Plan End | Actual Start | Actual End | Status | Completion outlook | Remarks
1 | Engine Tilt test | LAB | 2026-06-01 | 2026-06-03 | 2026-06-02 | 2026-06-03 | Completed |  | Test done with 35 degree
2 | LCCT | LAB | 2026-06-10 | 2026-08-31 | 2026-06-20 |  | Likely Delay | 2026-09-10 | Started with delay due to test bed non-availability
3 | RDT | LAB | 2026-07-01 | 2026-09-30 | 2026-07-01 |  | In Progress | 2026-09-30
4 | TT | Test track | 2026-07-01 | 2026-09-30 |  |  | Yet to Start
5 | Durability -1000 Hours | Field | 2026-08-01 | 2026-10-31 |  |  | Yet to Start
6 | OCT | LAB | 2026-08-01 | 2026-08-10 |  |  | Yet to Start