## Sheet1
[7 empty] | L0 Drawing release |  |  | CAE Analysis |  |  | L1 Drawing release |  |  | L2 Drawing release
S.No | System | Part Number | Part Description | Part Category | Commodity | Design Engineer | Plan | Actual | Status | Plan | Actual | Status | Plan | Actual | Status | Plan | Actual | Status
1 | CCV | F8S01422 | Crankcase | HIHR | Casting | Arun | 2026-03-15 |  | Pending | 2026-05-14 |  | Pending | 2026-05-29 |  | Pending | 2026-11-25 |  | Pending
2 | Intake | F8S01522 | Intake Manifold | MIMR | Al Casting | Sujitha | 2026-02-28 |  | Pending | 2026-04-29 |  | Pending | 2026-05-14 |  | Pending | 2026-11-10 |  | Pending
3 | Exhaust | F8S01533 | Exhaust Manifold | LILR | Casting | Gokul | 2026-02-28 |  | Pending | 2026-04-29 |  | Pending | 2026-05-14 |  | Pending | 2026-11-10 |  | Pending
4 | Exhaust | F8S01544 | Turbocharger | MIMR | Proprietary | Gokul | 2026-03-31 |  | Pending | 2026-05-30 |  | Pending | 2026-06-14 |  | Pending | 2026-12-11 |  | Pending
5 | Intake | F8S01555 | Intake throttle valve | HIHR | Proprietary | Arun | 2026-03-21 |  | Pending | 2026-05-20 |  | Pending | 2026-06-04 |  | Pending | 2026-12-01 |  | Pending
Formulas:
CAE Analysis = [L0 Drawing release]+60
L1 Drawing release = [CAE Analysis]+15
L2 Drawing release = [L1 Drawing release]+180