## Sheet1
Build Phase | Location | Planned Quantity | Actual Quantity | Plan Dates | Actual Dates | Status
EP | MRV | 10 | 5 | 2026-06-01 | 2026-06-04 | Completed
EP | MRV |  |  | 2026-06-08 |  | In Progress
EP | MRV |  |  | 2026-06-15 |  | Yet to Start
EP | MRV |  |  | 2026-06-22 |  | Yet to Start
EP | MRV |  |  | 2026-06-29 |  | Yet to Start
Gen1 | Nagpur | 10 |  |  |  | Yet to Start
Gen2 | Nagpur | 10 |  |  |  | Yet to Start
PP1 | Nagpur | 15 |  |  |  | Yet to Start
PP2 | Nagpur | 15 |  |  |  | Yet to Start
SOP | Nagpur | 50 |  |  |  | Yet to Start
Formulas:
Plan Dates = [Plan Dates, row above]+7